## Slide 1
Getting from Here to There
Thomas Murray
Vice President of Customers and Communities

## Slide 2: Vermont Gas Project Background
Vermont Gas completed a 41 mile
pipeline expansion in 2017
The most controversial Vermont
energy project in a decade

## Slide 3: Project Challenges
Cost Increase ~$90m to $165m ($30m WO)
ROW (165 Landowners/Only 1 Eminent Domain)
Regulatory/Political
Protestor/Media
Company Image/Brand Tarnishing
Organizational/Employee Morale/Turn Over
Project Management/Contractors

## Slide 4: Protest Culture
Passionate opposition to Fossil Fuel infrastructure
Landowners opposed easements
Engaged local energy groups
Symbolic Climate Change Solution
Social Media/24 Hour News
Demographics-Young and Old

## Slide 5: Company Image Under Assault

## Slide 6: Protest Activities
Tree sitters
People chained to pipeline/equipment
Blocked access to pipe yard
Roof top access at VGS
Shut down of State Street, Montpelier
Protests at state and local hearings
Demonstrations at CEO and State Official homes.

## Slide 7: We’re not alone, wind and solar projects rejected

## Slide 8: What does success look like?

## Slide 9: Lessons Learned
Engage key stakeholders-early and often
Develop grassroots champions
Prepare for this project to run your business and life (for years)
Assemble an A+ Team with deep experience with pipeline projects of this size
Don’t believe your own BS, make sure you remain clear-eyed
Expect/Plan for success, prepare for failure
It has to be perfect…..compliance and accuracy at levels way above normal
Respect right to protest/maintain calm demeanor
Streamline media interactions/generate positive press (FOIA)

## Slide 10
Questions